## Sheet 1
Table 1
App review
17/05/20
Library
| Issue | Wireframe |  | Complexity | Status
S-small; M-medium;large
| The font style at the top for library should be the same as the lounge – it should be in blue and on the left of the page. Also the font size for library & lounges should be the same... font size should be larger for library .. |  |  | S
| Dashboard at the top should not have lifestyle as a category, it should be the news. |  |  | S
| The news section needs to feed the dashboard at the top |  |  | M
| The dashboard should be a hyper link to the contents at the bottom |  |  | S
| For the search functionality can we change the words “All list” to “Full library” |  |  | S
| News section – can we take out the words visit website. Just clicking on the box should take the user to the news sites. |  |  | S
| News section should have pictures (still outstanding) |  |  | M
| Contents need to be in the right sections |  |  | M
| Footprints of grace should be the only book that has a price (to test stripe) and will send the cover of the book again |  |  | M
| We need to activate full stripe compatibility end to end. |  |  | M
Dashboaard
| Issue | Wireframe |  | Complexity | Status
Profile sections
| First name and last name needs to be populated as a mandatory field – this needs to be enforced |  |  | M
I see that the username is showing as the profile name which is correct
| Allocated time should come before reading interest allocation |  |  | S
Add friends
| Delete Invite by email or phone |  |  | S
| we need a search functionality, it needs to pull contacts first and last name in alphabetical order, right now it is displaying email addresses |  |  | M
| The invite a friend functionality is not working. I keep getting an error message. Also, Tomi is already on the app and we still can’t connect as friends |  |  | M
Lounge
| Issue | Wireframe |  | Complexity | Status
| We need to have all contents in the right lounge |  |  | S
| We need to find a way to hide the news feature in the lounge |  |  | S
We have a news lounge where we can put the news
| The library section says Library of the Football – can it just have Football as the header ad delete “library of the” |  |  | S
| Its only from the selected books in the lounge that the user can create a plan which pops up at the bottom |  |  | S
| Please note that after he has fed just the contents in the lounge we shouldn’t see other reference books. Please ensure there is a logic to stop a book showing in the wrong lounge |  |  | S
Plans
| Issue | Wireframe |  | Complexity | Status
| We can’t see the list of users in the plan, in the same way we can see it in the lounge, can we have a way to click on the icon to display who has joined the lounge |  |  | S
| For instance – in the faith lounge busisod, savvy reader and ladisod are members which tells us there are 3, however the book plan dream big talk big has 3 but when I click on the book icon I see Nigel is able to make comments but he isnt a member of the lounge |  |  | S
| When I click on the plan details – and see the members I see names such as lucky, Capitan and Flame – which tells me its not yet integrated and functional. |  |  | M
| Also there are two headers in the tab here – Plan Details and Details – can we delete the non functional header |  |  | S
| I cant see invite a friend in the plan details |  |  | S
| Activity feeds still says left a comment to the fragment and as discussed should have a hyperlink or page / chapter on where this comment is |  |  | M
| Chat functionality needs to activated |  |  | M
| The next tab which has Reviews – should be taking its feeds from the comment box at the top of the reader – we mentioned to rename to Reviews, because we have another comments box at the bottom. This is what should be feeding the activity wall , the review/comments box should be feeding the reviews section |  |  | M
Reader
| Issue | Wireframe |  | Complexity | Status
| The share button functionality should always reference readapp or create a hyperlink to the app because it is being sent outside the app and is a way to invite and ask new users to join. |  |  | S
| The highlight comments as discussed isn’t referenced to a chapter or page or best still create a hyper link |  |  | M
| The reader doesn’t have a font adjustment |  |  | S
| When a user taps on pause to stop reading, the reader does not remember where the user has stopped and takes them back to the beginning – this needs to be fixed |  |  | M
| Readers tend to have page numbers at the bottom /bookmarks |  |  | S
| Still pending – we need to assess how we deal with the blogs …. and group plans functionality. Can we load more comics and blogs - I need to decide end how this should be displayed. Sharigan has no colour and looks dull and I want to comare with other contents |  |  | M
Sent 07/05
Library
| Issue | Wireframe |  | Complexity | Status
| Newsfeed - filter to show just top 10, CNN, NBC, FOX, BBC, SKY, News Week, Business Insider, Aljazeera, ABC, Euronews (Backlog) |  |  | M
| Either work to have the pictures of the news stations show up or we feed the news to the dashboard , please lets create a news lounge too and have these listed in the exclusive areas. the plan should show CNN as its display |  |  | M
| Move the content into the right sections - all books should now move to books, blogs should have lucy's and editorials comics (i'll send more resources to add to the blogs and editorial sections |  |  | S
| we decided to leave the epub versions for now for blogs and editorials, it will create an issue which is where we need Kwasi to work on a solution where users can upload content themselves and we wont have to do the conversions. so at some point we must be able to use all files types by July |  |  | M
| i had sent a cover of my book and will send again |  |  | S
Lounge
| Issue | Wireframe |  | Complexity | Status
| we need the lounges populated with resources |  |  | S
| get group plans working effectively |  |  | M
| update all the cosmetic changes on the lounge as discussed |  |  | S